## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | swen-261-03-a-the_a_team
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | AN, 9 Oct
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | AN, 9 Oct
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | AN, 9 Oct
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | AN, 9 Oct
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | AN, 9 Oct
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | AN, 9 Oct
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | AN, 9 Oct
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | AN, 20 Oct, PASSED
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | AN, 20 Oct, PASSED
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | AN, 20 Oct, PASSED
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | AN, 20 Oct, PASSED
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | AN, 20 Oct, PASSED
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | AN, 20 Oct, PASSED
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | AN, 20 Oct, PASSED
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | AN, 20 Oct, PASSED
As a Player, I want to be able to sign out when I'm done playing. | Given that I am not in a game, there needs to be a button to click to sign out |  |  | Pass | AJ Nov 3, Passed
| Given that I am not in a game, when I click the sign out button, I am signed out |  |  | Pass | AJ Nov 3, Passed
| When I sign out, my name needs to become available again for login at another time. |  |  | Pass | AJ Nov 3, Passed
| Given that my connection drops or is interrupted, I need to be automatically signed out. |  |  | Pass | AJ Nov 3, Passed
As a player I want to be able to move diagonally so that I can make a move | Given that my piece is on the edge of the board, I should not be able to move off the board. |  |  | Pass | AJ Nov 3, Passed
| Given that it is my turn, I should be able to move. |  |  | Pass | AJ Nov 3, Passed
| Given that I click on a piece, then that one should be the one that is going to be moved. |  |  | Pass | AJ Nov 3, Passed
| Given that press the reset move button, my pieces should go back to their starting positions. |  |  | Pass | AJ Nov 3, Passed
| Given that I move a piece, I should get a message stating if my move is valid. |  |  | Pass | AJ Nov 3, Passed
| Given that it is not my turn, the game should refresh until my opponent submits their turn. |  |  | Pass | AJ Nov 3, Passed
As a player I want to be able to jump over my opponents’ piece so that I can capture it. | Given that there is an open space "behind" an opponent's piece that my piece is adjacent to, I can move that piece to the open space behind it. |  |  | Pass | AJ Nov 3, Passed
| Given that I have moved my piece "over" my opponent's piece, their piece is removed from the game. |  |  | Pass | AJ Nov 3, Passed
| Given that I have jumped over a piece, the process should go to the multiple jumps section. |  |  | Pass | AJ Nov 3, Passed
As a player I want to be able to perform multiple jumps so that I can capture multiple pieces. | Given that my piece has successfully jumped over my opponent's piece, there needs to be a check for other possible jumps. |  |  | Pass | AJ Nov 3, Passed
| Given that there is only one possible jump, then the next jump should be made and another check should occur. |  |  | Pass | AJ Nov 3, Passed
| Given that there are two or more possible jumps, there should be time for me to indicate which jump I would like to make. |  |  | Pass | AJ Nov 3, Passed
| Given that there are no other possible jumps, my turn should end. |  |  | Pass | AJ Nov 3, Passed
As a player I want to be able to if I can jump, once or multiple times, when I am required to so that I can conform to the rules of the game. | Given that it is my turn, there needs to be a check for possible jumps. |  |  | Pass | AJ Nov 3, Passed
| Given that there are possible jumps, the process should go to the jump sections. |  |  | Pass | AJ Nov 3, Passed
| Given that there are multiple pieces with possible jumps, then user should select which piece to jump with. |  |  | Pass | AJ Nov 3, Passed
As a player I want to be able to my king piece in any direction so that I can defeat my opponent | Given that my piece is crowned, when I move the piece I expect to be able to move toward both sides of the board. |  |  | Pass | AJ Nov 3, Passed
As a player I want my piece to be crowned so that I can win the game. | Given my piece is uncrowned, I move my piece into the row closest to my opponent, I expect that my opponent crowns my piece. |  |  | Pass | AJ Nov 3, Passed